## Sheet1
|  | Milestone | Action | Responsible | Start Date Goal | Dependancies | Date Completed
0 |  | Support activities |  | Ken
|  |  | Erect Shed | Ken/Kathy et al | 2005-09-27 |  | 2005-09-28
A |  | (Re)Plant Oak tree |  | Ken, Eleanor |  |  | 2005-07-06
B |  | Soil prep for Garden |  | Ken
B | 1 |  | Apply Gypsum 350 lb | Ken |  |  | 2005-07-19
B | 2 |  | Grape Pummice/Horse Manure Compost delivery (40 cuyrd) | Wente |  |  | 2005-07-22
B | 3 |  | Rototil/level | Ken/Ralph |  |  | 2005-07-22
B | 4 |  | ApplyFish emulsion (6G) | Ken |  |  | 2005-08-02
B | 5 |  | Re-rototill | Ken/Ralph | 2005-09-20 | B3+ 8weeks | 2005-09-20
B | 6 |  | Set up manual watering | Ken | 2005-09-28
B | 7 |  | ApplyFish emulsion | Ken/Erica | 2005-10-03
C |  | Collaboration Meeting with city /LARPD/County |  | Kathy | 2005-09-19
C | 1 |  | Create Presentation | Kathy | 2005-09-24 |  | 2005-09-27
C | 2 |  | Present to Sup Haggarty Staff | Kathy | 2005-09-28 |  | 2005-09-28
C | 3 |  | Present to City |  | n/r
C | 4 |  | Present to LARPD |  | n/r
C | 5 |  | Determine where we can get ext. resources | Chris Gary/ Mario Montalvo
D |  | Paint path/Irr Trench |  | Ken/Carol | 2005-10-17 | B | 2005-10-19
E |  | Auger Tree holes |  | external | Late Oct | resources, B
Ken to Contact Davey Tree
F |  | Install Irrigation |  | External/MG | Late Sept | D
F | 1 |  | Irrigation plan | Carol | 2005-09-20 |  | 2005-09-26
F | 2 |  | Trenching for PVC | County Maint | 2005-10-19 | C5,F1
F | 3 |  | Installation of irrigation stubs | MG Volunteers | 2005-11-05 | F2
F | 4 |  | Connect low flow irrigation to stubs | MG Volunteers | after planting | I
G |  | Pathways |  | External/MG | Early Oct | F
G | 1 |  | Cut paths | County Maint | 2005-10-20 | Resources, F3
G | 2 |  | Install Border | MG Volunteers |  | G1
G | 3 |  | Lay Grannite | External/MG |  | G2
G | 4 |  | Cut curb for Handicap access | County Maint | 2005-10-20 | Resources, G1
G | 5 |  | Pour concrete for ramp | External | 2005-10-20 | G5
h |  | Creekbed |  | External/MG | Early Oct | G
H | 1 |  | Grading for dry creek bed | External | Mid Oct | Resources,G
H | 2 |  | Large Boulder donation | External
H | 3 |  | Lay large boulders | External |  | H1,H2,F3
H | 4 |  | Lay moss rock and cobble | MG Volunteers |  | H2
I |  | Planting |  | MG Volunteers | Late Oct | G,F3,E
I | 1 |  | Create Buffer Berms | External/MG | Late Oct | G1
I | 2 |  | Plant Trees |  | Late Oct | E,G1,I1
I | 3 |  | Plant Butterfly /Hummingbird garden |  | Early Nov | G1,I2
I | 4 |  | Dry Creekbed |  | Early Nov | H,G2
I | 5 |  | Plant Under Oak |  | Early Nov | G2,I2
I | 6 |  | Wind garden |  | Early Nov | G2,I2
J |  | Mulch |  | Ken | Late Fall 2005 | I
|  |  | Contact Tree companies for tree chips | Ken
J | 1 |  | Shredded Redwood
J | 2 |  | Woodchips
J | 3 |  | Gravel
J | 4 |  | Compost/Leaf mold
K |  | Benches |  | Ken/Kathy | Spring 2006 | J
K | 1 |  | Find Community group interested in sponsoring |  |  | J
K | 2 |  | Install |  |  | J
L |  | Kiosks |  | Ken/Kathy | Spring 2006 | J